## Sheet1
PROJECT PLANNING |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3
Month |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Main Milestones |  | YEAR 1 6: MS1; YEAR 1 12: MS2; YEAR 2 18: MS3; YEAR 2 24: MS4; YEAR 3 30: MS5; YEAR 3 36: MS6
WOK PACKAGES
WP1 Project Management |  | YEAR 1 4: D1.1; YEAR 1 6: D1.2; YEAR 1 12: D1.3; YEAR 2 24: D1.4; YEAR 3 36: D1.5
T1.1 | Project assessment and adjustment
T1.2 | Project Reporting
T1.3 | Project Meeting
T1.4 | Financial and cost management
WP2 Requirements Analysis |  | YEAR 1 4: D2.1; YEAR 1 6: D2.2; YEAR 1 9: D2.3
T2.1 | Use case specification | bar: YEAR 1 1 to YEAR 1 6
T2.2 | State of the Art | bar: YEAR 1 1 to YEAR 1 4
T2.3 | High-level System Architecture | bar: YEAR 1 4 to YEAR 1 9
WP3 Proximity Detection and AI |  | YEAR 1 12: D3.1; YEAR 2 15: D3.2-D3.4; YEAR 2 18: D3.5-D3.6; YEAR 2 24: D3.7-D3.11
T3.1 | Proximity Detection | bar: YEAR 1 10 to YEAR 2 24
T3.2 | Proximity Interaction | bar: YEAR 1 10 to YEAR 2 24
T3.3 | User Localization | bar: YEAR 2 15 to YEAR 2 24
T3.4 | User Intention | bar: YEAR 1 10 to YEAR 2 24
T3.5 | Proximity Service Selection | bar: YEAR 2 13 to YEAR 2 24
WP4 SW Framework Architecture |  | YEAR 1 12: D4.1; YEAR 2 18: D4.2-D4.4; YEAR 2 24: D4.5-D4.7; YEAR 3 30: D4.8-D4.10
T4.1 | SW Architecture Design Refinement | bar: YEAR 1 10 to YEAR 1 12; YEAR 2 19 to YEAR 2 21; YEAR 3 25 to YEAR 3 27
T4.2 | Client-side Platform | bar: YEAR 2 13 to YEAR 2 18; YEAR 2 21 to YEAR 2 24; YEAR 3 27 to YEAR 3 30
T4.3 | Server-side Platform | bar: YEAR 2 13 to YEAR 2 18; YEAR 2 21 to YEAR 2 24; YEAR 3 27 to YEAR 3 30
T4.4 | Programming Models | bar: YEAR 2 13 to YEAR 2 24
T4.5 | Testing Tools | bar: YEAR 2 19 to YEAR 2 24
T4.6 | Deployment Tools | bar: YEAR 3 25 to YEAR 3 30
WP5 Security and Privacy |  | YEAR 1 12: D5.1; YEAR 2 15: D5.2; YEAR 2 18: D5.3; YEAR 2 24: D5.4; YEAR 3 30: D5.5; YEAR 3 33: D5.6
T5.1 | Security and Privacy Requirements | bar: YEAR 1 10 to YEAR 1 12
T5.2 | Security and Privacy Design | bar: YEAR 2 13 to YEAR 2 15
T5.3 | Security and Privacy Implementation | bar: YEAR 2 16 to YEAR 2 24
T5.4 | Security and Privacy Review | bar: YEAR 3 25 to YEAR 3 27; YEAR 3 31 to YEAR 3 33
WP6 Demonstration and Validation |  | YEAR 2 18: D6.1; YEAR 2 24: D6.2; YEAR 3 30: D6.3; YEAR 3 34: D6.4
T6.1 | Use case specification
T6.2 | Use case design
T6.3 | Use case implementation
T6.4 | Use case testing and validation
T6.5 | Use case evaluation
WP7 Dissemination, Exploitation, Communication |  | YEAR 1 10: D7.1-D7.2; YEAR 2 22: D7.3; YEAR 3 34: D7.4
T7.1 | Dissemination
T7.2 | Exploitation of Results
T7.3 | Communication