## Tasks
PROJECT PLANNING |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3
Month |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Main Milestones |  | YEAR 2 17: MS1; YEAR 2 24: MS2; YEAR 3 28: MS3; YEAR 3 32: MS4; YEAR 3 36: MS5
WP1 Project Management
T1.1 | Project assessment and adjustment
T1.2 | Project Reporting
T1.3 | Project Meeting
T1.4 | Financial and cost management
WP2 Requirements Analysis | bar: YEAR 1 1 to YEAR 2 17
T2.1 | Use Case Specification
T2.2 | State of the Art
T2.3 | High-level System Architecture
WP3 SW Framework Architecture | bar: YEAR 1 7 to YEAR 2 24
T3.1 | SW Architecture Design Refinement
T3.2 | Client-side Platform
T3.3 | Server-side Platform
T3.4 | Programming Models
T3.5 | Testing Tools
T3.6 | Deployment Tools
WP4 Proximity Detection and AI | bar: YEAR 1 7 to YEAR 3 28
T4.1 | Proximity Detection
T4.2 | Proximity Interaction
T4.3 | User Localization
T4.4 | User Intention
T4.5 | Proximity Service Selection
WP5 Security and Privacy | bar: YEAR 2 13 to YEAR 3 32
T5.1 | Security and Privacy Requirements
T5.2 | Security and Privacy Design
T5.3 | Security and Privacy Implementation
T5.4 | Security and Privacy Review
WP6 Demonstration and Validation | bar: YEAR 2 13 to YEAR 3 36
T6.1 | Use case specification
T6.2 | Use case design
T6.3 | Use case implementation
T6.4 | Use case testing and validation
T6.5 | Use case evaluation
WP7 Dissemination, Exploitation, Communication
T7.1 | Dissemination
T7.2 | Exploitation of Results
T7.3 | Communication

## Deliverables
PROJECT PLANNING |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3
Month |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Main Milestones |  | YEAR 2 17: MS1; YEAR 2 24: MS2; YEAR 3 28: MS3; YEAR 3 32: MS4; YEAR 3 36: MS5
WP1 Project Management
D1.1 | Project Plan | YEAR 1 6: D1.1; YEAR 2 17: D1.1; YEAR 2 24: D1.1; YEAR 3 28: D1.1; YEAR 3 32: D1.1
D1.2 | Annual Reports | YEAR 1 12: D1.2; YEAR 2 24: D1.2; YEAR 3 36: D1.2
WP2 Requirements Analysis | bar: YEAR 1 1 to YEAR 2 17
D2.1 | Use Case Specification | YEAR 2 17: D2.1
D2.2 | State of the Art | YEAR 2 17: D2.2
D2.3 | System Architecture (High Level View) | YEAR 2 17: D2.3
WP3 Software Framework Architecture | bar: YEAR 1 7 to YEAR 2 24
D3.1 | System Architecture Document (Detailed View) | YEAR 2 24: D3.1
D3.2 | Proximity Services Framework Implementation (SW) | YEAR 2 24: D3.2
WP4 Proximity Detection and AI | bar: YEAR 1 7 to YEAR 3 28
D4.1 | System Architecture Document (Proximity Detection and AI) | YEAR 3 28: D4.1
D4.2 | Proximity Detection and AI Implementation (SW) | YEAR 3 28: D4.2
WP5 Security and Privacy | bar: YEAR 2 13 to YEAR 3 32
D5.1 | System Architecture Document (Security & Privacy) | YEAR 3 32: D5.1
D5.2 | Security and Privacy Implementation (SW) | YEAR 3 32: D5.2
WP6 Demonstration and Validation | bar: YEAR 2 13 to YEAR 3 36
D6.1 | Demonstration and Validation Plan | YEAR 2 24: D6.1; YEAR 3 32: D6.1
D6.2 | Test Document (Test Cases and Results) | YEAR 2 24: D6.2; YEAR 3 28: D6.2; YEAR 3 32: D6.2; YEAR 3 36: D6.2
WP7 Dissemination, Exploitation, Communication
D7.1 | Public Web Site | YEAR 2 17: D7.1
D7.2 | Dissemination & Exploitation Plan | YEAR 2 17: D7.2; YEAR 2 24: D7.2; YEAR 3 28: D7.2; YEAR 3 32: D7.2; YEAR 3 36: D7.2
D7.3 | Dissemination & Exploitation Report | YEAR 3 36: D7.3
Note on S5: Sinan Ozmen: Update
Note on Z5: Sinan Ozmen: Update
Note on AD5: Sinan Ozmen: Update
Note on AH5: Sinan Ozmen: Update
Note on AH21: Sinan Ozmen: Update
Note on AD22: Sinan Ozmen: Update
Note on AH22: Sinan Ozmen: Update
Note on AL22: Sinan Ozmen: Update
Note on Z25: Sinan Ozmen: Update
Note on AD25: Sinan Ozmen: Update
Note on AH25: Sinan Ozmen: Update
Note on AL25: Sinan Ozmen: Update